## Status
Sl.No | Activity | Description | Priority | Status | Comments
1 | Revamp Admin Module | Make changes to Admin Module as per feedback |  | WIP | 1st version given for testing
2 | Test Admin Module |  |  | Complete | Issue List given
3 | Enhance Student Module | Make changes to Student Module as per changes in Admin Module |  | Not Started
4 | Student Module - UI | Change UI for Student Module |  | Not Started
5 | Resume Builder | Development of Resume Buidling |  | WIP
6 | E2E - Resume Builder | Integrate Resume Builder to Elixir |  | Not Started
6 | E2E - Resume Builder | Document Resume Builder Solution |  | Not Started
7 | E2E - Aptitude | Development of Aptitude test module |  | Not Started
8 | E2E - Aptitude | Design and Document Aptitude Test Solution |  | Not Started
9 | Student Module | Help Content to be integrated |  | Not Started
10 | Admin Module - Reports | Create reports |  | Not Started
11 | Prod Set-up | Set up Prod Environment in Creating Futures Domain |  | WIP
12 | Issue fixing | Fixing issue for the next release |  | ?? | Can we plan for releasing the changes

## Issue List
Sl.No | Topic | Desc | screen | Status
1 | Type of Q | Remove the Following from the dropdown 1. Match the Following 2. Crosswords 3. Word Search | Add Questions | Done
2 | Order of Columns | The columns should be in the following Order 1. Program 2. Module 3. Level 4. Type of Question 5. Narrative 6. Question 7. Options (where applicable) 8. Answer 9. Hint 10. Comments | Add / Edit Questions | Done
3 | Mandatory Field | For Answer, put a red asterix | Add / Edit Questions | Done
4 | Number of records | Display 10 records per screen | View Questions | Done
5 | Display of fields | Not all fields are shown when viewing a question | View Questions | Done
6 | Back Button | Add a "Back" button | View Questions | Done
7 | Edit Q | All fields that are there in "Add Questions" should be shown in Edit | Edit Questions | Done
8 | Display all Pages | In the initial page, it is showing only 2 pages. Can you show all the pages | View Questions | Done
9 | Edit Q | Add a "Cancel" button | Edit Questions | Done
10 | Export Questions | Export questions in xls format | Export Questions | Need Changes
11 | Search | Is there a possibility to do a search based on questions | View Questions | No
12 | 3 options shown | For multiple choice questions, only 3 options are shown | Edit Questions | Done
13 | Audio Q | While viewing an audio question,other questions that are not part of this question also is shown | View Questions | Done | Please check for the same issues for Video Questions
14 | Audio Q | While viewing an audio question, not able to play the audio | View Questions | Done
15 | Audio Q | Can you please show the name of the file that has been uploaded | Edit Questions | Done
16 | Audio Q | How do I add additional Questions for an audio file? I remember you saying that there will be a change here | Add Questions | Done
17 | Single Image | Image is not seen | View & Edit Questions | Done
18 | Single Image | Google Translate - French is appearing | View Questions | Done
19 | Single Image | Can you please show the name of the file that has been uploaded | Edit Questions | Done
20 | Single Image | Not able to save the change | Edit Questions | Done
21 | Text | While viewing a text question,other questions that are not part of this question also is shown | View Questions | Done
22 | Text | Can you please show the name of the file that has been uploaded | View & Edit Questions | Done
23 | Text | Question Text and Current columns are shown | Edit Questions | Done
24 | Text | Not able to save the change | Edit Questions | Done
25 | Code Correction | Questions / Modulues /programs are related using database Id. Need to create unique code | Releation in code
26 | Navigation | Restructure the navigation approach | Student Module
27 | Questions | Right regrouping of questions based on templates - Approach to be relooked | Student Module
28 | Logs | Need to enable logs to help debugging | Whole application
29 | Filters in View | Can we have filters in the Question Views? | View Questions
30 | CSS Template | the CSS template for View screens have to be changed | Admin Module

## Tasks
Task |  | Owner | Interns Tasks
Alternative QA enviornment | Redhat/Oracle | Internal | Issues Fix that are idenfied in the Admin module
Production enviornement setup |  | Internal | Navigation of student module / Issues
Tehnical flow documents |  | Arpit | Enable logging - Application to be made debug ready
How to migration QA data |  | Internal | E2E module - Resume builder integration
E2E module - Aptitude test
Mobile POC
Students module Spoken English (Based on question type)

## All modules
| Module | Requirements | Design | Development | Testing | Release
Spoken English | Admin | Done | Done | In Progress | In Progress
| Student | Done | done | In Progress | In Progress
E2E | Resume Builder | Done | To Do | To Do
| Aptitude Test | ToDo
| Logical Reasoning | ToDo